## Slide 1: Visualizing Peer-to-Peer Networks
Midterm (Iteration 1) Design Review Presentation
By Team SPEW

## Slide 2: Team Members
Chris Sidi (Project Manager)
Bill Phillips (Developer)
Jimmy Espana (Documentation)
Eric Withrow (Developer)

## Slide 3: Why are we called Team SPEW ?
  Sidi
Phillips
Espana
Withrow

## Slide 4: Customer & Faculty Advisor
Customer: Dr. Brian Cooper
Faculty Advisor: Dr. Brian Cooper

## Slide 5: The Goal
Add visualization component to a peer-to-peer toolkit called ODIN.
ODIN = Overlay-Dynamic Information Networks
    A peer-to-peer toolkit (www.cc.gatech.edu/~cooperb/odin/)
Long Term Goal - Extend ODIN into a debugging toolkit that can be used to analyze, and possible troubleshoot Peer-to-Peer Networks.

## Slide 6: Before

## Slide 7: After

## Slide 8: Customer Background
Peer-to-peer networks are moving beyond music filesharing and becoming popular platforms for building a variety of distributed applications.
Although many P2P systems are being built, it is difficult to get a good understanding of how they are actually performing and compare them.

## Slide 9: Customer Background (cont.)
Would like us to build a visualization tool that allows us to present a simulation of a peer-to-peer network.
  Which regions of the network are experiencing heavy or light traffic.
  Which regions of the network are generating heavy or light traffic.
  Visualize graphically how an individual message gets routed through the network, hopefully.

## Slide 10: Overview of Requirements
The ODIN visualization tool that we will develop / deliver will have the following supporting features:
  Display network topology.
  Visualize a running simulation of the network.
  Inspect a specific peer within the network.
  Ability to analyze points of congestion.
  Ease of use.

## Slide 11: Example Use Case
Run complete ODIN Simulation.
Open visualization tool.
Load log file.
Network topology displayed and modified over time.
User chooses new focus node or graph layout.

## Slide 12: Design Alternatives
We considered two architectures:
  An Event Driven Architecture
    In which events from ODIN are fed automatically into the Visualization GUI via network connections.
  A Pipe and Filter Architecture
    In which the flow of logging data, from the simulation, could be converted into a input form that would be graphically displayed.

## Slide 13: Architecture Rationale
We decided not to chose the Event Driven Architecture because of network traffic overhead.
The Pipe and Filter Architecture works better because of the natural flow of logging data from the simulation. The log data can then be visually displayed after the simulation has finished.

## Slide 14: Architecture Rationale (cont.)

## Slide 15: Status Report
Our project is running smoothly; on track.
No major Issues have occurred so far.
Possible “Show Stoppers”.
All major milestones have been met for first iteration.

## Slide 16: Show Stoppers
Issue: No access to CoC clusters first couple of weeks of semester.
Action: Confronted CNS in regard to this problem.
Impact: ODIN research delayed for 2 weeks, work shifted to design

## Slide 17: Resources (Person-Hours)

## Slide 18: Features and Artifacts

## Slide 19
Iteration 1 Demo

## Slide 20: Future Iteration Plans
Link activity.
Identifying areas of congestion.
More advanced radial graphing techniques (constructing better BFS trees).
Other graph layouts.

## Slide 21: The End
Questions or Comments?

## Slide 22: Iteration 1 Backlog
Days Left In Iteration |  | 21 | 14 | 7 | 0 | End Iter. 1
Who | Description | 1/23/2006 | 1/30/2006 | 2/6/2006 | 2/13/2006 | Totals
Jimmy | Product Vision | 0 | 0 | 0 | 15 | 15
Jimmy | Product Backlog | 0 | 0 | 0 | 3 | 3
Jimmy | Iteration 1 Backlog | 0 | 0 | 0 | 5 | 5
Jimmy | Status Reports | 1 | 2 | 3 | 3 | 9
Chris | Understand/study ODIN | 10 | 10 | 0 | 0 | 20
Eric, Bill, Chris | Initial Graph Layout Exploration | 15 | 15 | 10 | 10 | 50
Jimmy, Chris, Bill, Eric | Use Cases | 0 | 12 | 0 | 0 | 12
Jimmy, Chris, Bill, Eric | High-Level Design Doc | 0 | 0 | 16 | 0 | 16
Eric, Chris, Bill | Actual ODIN-driven topology display, any layout | 8 | 6 | 6 | 6 | 26
Jimmy, Chris, Bill, Eric | Midterm Presentation | 0 | 0 | 4 | 10 | 14
Total Estimated Hours Remaining |  | 160 | 120 | 80 | 40 | 0

## Slide 23: Project Backlog
Priority | Item# | Description | Estimate | Estimated By
 | 1 | Product Vision | 15 | Jimmy
Very High | 2 | Product Backlog | 3 | Chris
 | 3 | Iteration 1 Backlog | 5 | Chris
 | 4 | Status Reports | 7 | Jimmy
 | 5 | Understand/study ODIN | 20 | Chris
 | 6 | Initial Graph Layout Exploration | 50 | Chris
High | 7 | Use Cases (Iteration 1 subset) | 12 | Chris
 | 8 | High-Level Design Doc | 16 | Chris
 | 9 | Actual ODIN-driven topology display, any layout | 26 | Chris
 | 10 | Midterm Presentation | 14 | Chris
Medium | 11 | Reflect activity levels on links | 10 | Chris
 | 12 | An intuitive layout | 30 | Chris