## CS 4911
Assignment | Worth | My Grade | Avg Grade
Status Reports | 3% | 100% | 100%
Project Planning | 4% | 37.5% | 75.42%
Project Requirements | 10% | 81.25% | 81.39%
Project Design | 14% | 91% | 90%
Iteration 2 Design Review and Demo | 5% | 95% | 89.77%
System Acceptance Test Plan and Report | 5% | 83.33% | 89.33%
Midterm (Iteration 2) Design Review Presentation | 5% | 95% | 91.96%
Final Presentation and Demo | 10%
Delivery Documentation | 4%
Individual Design Analysis | 10%
Customer Delivery/Advisor Grade | 30%
Total | 100% | 39.03% | 40.31%
Task | Date | Hours | Cumulative | Cumulative x4 | Burndown
Initial meeting w/ Brian Cooper | 2006-01-20 | 2 | 2 | 8 | 692
graphviewer proof of concept | 2006-01-21 | 4 | 6 | 24 | 676
Hashtable graphviewer design (improved efficiency) | 2006-01-21 | 4 | 10 | 40 | 660
graphviewer code cleanup, improve efficiency | 2006-01-22 | 3 | 13 | 52 | 648
graphviewer - command executer & sim speed | 2006-01-25 | 4 | 17 | 68 | 632
Graph Layout research | 2006-01-25 | 1 | 18 | 72 | 628
Design and Documentation Meeting | 2006-01-26 | 2 | 20 | 80 | 620
Graph Arrangement, emails | 2006-01-29 | 2.5 | 22.5 | 90 | 610
Meeting, applet work, emails | 2006-01-31 | 2 | 24.5 | 98 | 602
Meeting - Use Cases | 2006-02-04 | 2.5 | 27 | 108 | 592
graphviewer - tried to get radial working | 2006-02-05 | 5 | 32 | 128 | 572
Meeting - Initial Conceptual Design | 2006-02-07 | 3 | 35 | 140 | 560
Visualization UML Sequence Diagram | 2006-02-08 | 1 | 36 | 144 | 556
Meeting with Cooper, discuss things | 2006-02-09 | 1 | 37 | 148 | 552
graphviewer pre-radial work | 2006-02-10 | 1.5 | 38.5 | 154 | 546
graphviewer radial working | 2006-02-16 | 5 | 43.5 | 174 | 526
Pre-Presentation Meeting | 2006-02-17 | 2 | 45.5 | 182 | 518
graphviewer - getting ready for demo | 2006-02-18 | 9 | 54.5 | 218 | 482
Presentation Practice | 2006-02-20 | 2 | 56.5 | 226 | 474
Presentation Practice | 2006-02-21 | 1 | 57.5 | 230 | 470
Meeting with Cooper | 2006-02-24 | 0 | 57.5 | 230 | 470
Use Case Iteration 2 Meeting | 2006-03-03 | 2 | 59.5 | 238 | 462
Worked on Test Plan | 2006-03-04 | 1.5 | 61 | 244 | 456
Slow-in Slow-out transitions | 2006-03-05 | 2 | 63 | 252 | 448
Reading gzip logs | 2006-03-06 | 3.5 | 66.5 | 266 | 434
Preliminary link congestion & code cleanup | 2006-03-07 | 4 | 70.5 | 282 | 418
Fixing Error conditions, info box on right | 2006-03-08 | 3.5 | 74 | 296 | 404
Added global log data to info box, node coloring | 2006-03-10 | 1.5 | 75.5 | 302 | 398
Meeting with cooper, architecture - iteration 2 | 2006-03-10 | 3.5 | 79 | 316 | 384
Fixing up design rationale | 2006-03-13 | 1 | 80 | 320 | 380
Pre-processor UML | 2006-03-14 | 1 | 81 | 324 | 376
Implementing GUI | 2006-03-18 | 7.5 | 88.5 | 354 | 401
Switched from SpringGUI to MyGui | 2006-03-19 | 2 | 90.5 | 362 | 393
Fixing MyGUI bugs | 2006-03-21 | 2 | 92.5 | 370 | 385
Making GUI pretty | 2006-03-21 | 5 | 97.5 | 390 | 365
Efficiency improvements related to transitions | 2006-03-22 | 3 | 100.5 | 402 | 353
Finishing touches on MyGUI elements | 2006-03-22 | 3.5 | 104 | 416 | 339
Polishing GUI, fixing link colors | 2006-03-23 | 4 | 108 | 432 | 323
Link Thresholds | 2006-03-23 | 2 | 110 | 440 | 315
Node Sizes and byteToString | 2006-03-24 | 3 | 113 | 452 | 303
Color scheme, link colors, minor tweaks | 2006-03-25 | 4 | 117 | 468 | 287
Performance tweaks, bug fixes | 2006-03-25 | 2 | 119 | 476 | 279
Keybinding and zoomslider improvements | 2006-03-26 | 1 | 120 | 480 | 275
Polar transitions | 2006-03-28 | 1 | 121 | 484 | 271
Meeting with Cooper | 2006-03-31 | 2 | 123 | 492 | 263
radialDirty, break, step | 2006-04-05 | 4.5 | 127.5 | 510 | 245
Meeting for use cases - iteration 3 | 2006-04-07 | 2 | 129.5 | 518 | 237
Code Cleanup | 2006-04-09 | 2 | 131.5 | 526 | 229
Finished breaking, stepping, resuming, GUI labels | 2006-04-11 | 4.5 | 136 | 544 | 211
Seek to timestamp, advanced controls | 2006-04-13 | 6 | 142 | 568 | 187
Meeting with Cooper | 2006-04-14 | 1.5 | 143.5 | 574 | 181
Updating Test Plan and Report | 2006-04-16 | 3.5 | 147 | 588 | 167
Fixing Test Plan and Report | 2006-04-19 | 1 | 148 | 592 | 163
Scouting, Meeting, User Testing | 2006-04-21 | 3 | 151 | 604 | 151
Network Viewer bug, cosmetic fixes | 2006-04-21 | 1.5 | 152.5 | 610 | 145
User Manual | 2006-04-23 | 3 | 155.5 | 622 | 133
Presentation Practice | 2006-04-24 | 3 | 158.5 | 634 | 121
Individual Design Analysis | 2006-04-25 | 3 | 161.5 | 646 | 109
Expected | 2006-04-30 | 25 | 186.5 | 746 | 9
Sum | n/a | 186.5
Meetings | Date | Hours | Total x4 | Total Cumulative
Initial w/ Brian Cooper | 2006-01-20 | 2 | 8 | 8
Design & Documentation | 2006-01-26 | 2 | 8 | 16
Quick Briefing & Planning | 2006-01-31 | 0.5 | 2 | 18
Use Cases | 2006-02-04 | 2.5 | 10 | 28
Initial Conceptual Design | 2006-02-07 | 3 | 12 | 40
Meeting with Cooper | 2006-02-09 | 1 | 4 | 44
Pre-Presentation Meeting | 2006-02-17 | 2 | 8 | 52
Presentation Practice | 2006-02-20 | 2 | 8 | 60
Presentation Practice | 2006-02-21 | 1 | 4 | 64
Meeting with Cooper | 2006-02-24 | 1 | 4 | 68
Use Case Iteration 2 Meeting | 2006-03-03 | 2 | 8 | 76
Meeting with cooper, architecture - iteration 2 | 2006-03-10 | 3.5 | 14 | 90
Meeting with Cooper | 2006-03-31 | 2 | 8 | 98
Use Cases for Iteration 3 | 2006-04-07 | 2 | 8 | 106
Meeting with Cooper | 2006-04-14 | 1.5 | 6 | 112
Meeting, User Testing | 2006-04-21 | 2 | 8 | 120
Total | n/a | 30 | 120
Status Report Hours for Week: | Date | Planned | Actual | Planned Cumulative | Actual Cumulative
1 | 2006-01-09 | 0 | 1 | 0 | 1
2 | 2006-01-16 | 6 | 7 | 6 | 8
3 | 2006-01-23 | 40 | 40 | 46 | 48
4 | 2006-01-30 | 40 | 50 | 86 | 98
5 | 2006-02-06 | 40 | 55 | 126 | 153
6 | 2006-02-13 | 40 | 40 | 166 | 193
7 | 2006-02-20 | 40 | 40 | 206 | 233
8 | 2006-02-27 | 40 | 48 | 246 | 281
9 | 2006-03-06 | 40 | 58 | 286 | 339
10 | 2006-03-13 | 40 | 67 | 326 | 406
Spring Break | 2006-03-20 | 40 | 40 | 366 | 446
12 | 2006-03-27 | 40 | 52 | 406 | 498
13 | 2006-04-03 | 40 | 54 | 446 | 552
14 | 2006-04-10 | 40 | 57 | 486 | 609
15 | 2006-04-17 | 40 | 54 | 526 | 663
16 | 2006-04-24 | 40 | 40 | 566 | 703
Total | n/a | 566 | 703