## Sheet1
Days Left In Iteration |  | 21 | 14 | 7 | 0 | End Iter. 2
Who | Description | 2006-02-27 | 2006-03-06 | 2006-03-13 | 2006-03-27 | Totals
Jimmy | Iteration 2 Backlog | 4 | 0 | 0 | 0 | 4
Chris, Bill, Eric | Iteration 2 Use Cases (Detailed) | 6 | 0 | 0 | 0 | 6
Jimmy, Eric | System Acceptance Test Plan | 0 | 6 | 0 | 0 | 6
Jimmy, Chris, Bill, Eric | Iteration 2 Design (Updated) | 0 | 0 | 8 | 0 | 8
Eric | Link Activity | 10 | 10 | 10 | 0 | 30
Bill | Preprocessor | 5 | 5 | 5 | 5 | 20
Chris, Bill, Eric | Extending ODIN | 0 | 0 | 0 | 5 | 5
Chris, Bill, Eric | Spring Layout Metrics | 5 | 0 | 5 | 0 | 10
Chris, Bill, Eric | Spring Layout | 10 | 5 | 5 | 5 | 25
Chris, Bill, Eric | H3 | 5 | 5 | 10 | 5 | 25
Jimmy, Chris, Bill, Eric | Usablilty Testing | 0 | 0 | 5 | 5 | 10
Jimmy, Chris, Bill, Eric | Customer Meetings | 5 | 5 | 0 | 0 | 10
Jimmy | Status Reports | 1 | 1 | 1 | 1 | 4
Jimmy | Vision Statement | 0 | 0 | 5 | 5 | 10
Total Estimated Hours Remaining |  | 160 | 120 | 80 | 40 | 0
NOTE: Spring Break week of 03/20/2006