## Sheet1
Days Left In Iteration |  | 21 | 14 | 7 | 0 | End Iter. 1
Who | Description | 2006-01-23 | 2006-01-30 | 2006-02-06 | 2006-02-13 | Totals
Jimmy | Product Vision | 0 | 0 | 0 | 15 | 15
Jimmy | Product Backlog | 0 | 0 | 0 | 3 | 3
Jimmy | Iteration 1 Backlog | 0 | 0 | 0 | 5 | 5
Jimmy | Status Reports | 1 | 2 | 3 | 3 | 9
Chris | Understand/study ODIN | 10 | 10 | 0 | 0 | 20
Eric, Bill, Chris | Initial Graph Layout Exploration | 15 | 15 | 10 | 10 | 50
Jimmy, Chris, Bill, Eric | Use Cases | 0 | 12 | 0 | 0 | 12
Jimmy, Chris, Bill, Eric | High-Level Design Doc | 0 | 0 | 16 | 0 | 16
Eric, Chris, Bill | Actual ODIN-driven topology display, any layout | 8 | 6 | 6 | 6 | 26
Jimmy, Chris, Bill, Eric | Midterm Presentation | 0 | 0 | 4 | 10 | 14
Total Estimated Hours Remaining |  | 160 | 120 | 80 | 40 | 0