## Sheet1
Days Left In Iteration |  | 21 | 14 | 7 | 0 | End Iter. 3
Who | Description | 2006-04-03 | 2006-04-10 | 2006-04-17 | 2006-04-24 | Totals
Jimmy | Iteration 3 Backlog | 5 | 0 | 0 | 0 | 5
Chris, Bill, Eric | Iteration 3 Use Cases (Detailed) (Final Use Cases) | 0 | 7 | 0 | 0 | 7
Eric | System Acceptance Test Report | 0 | 0 | 7 | 0 | 7
Chris, Bill, Eric | Iteration 3 Design (Updated) | 0 | 0 | 5 | 0 | 5
Jimmy, Chris, Bill, Eric | Final Vision Document | 0 | 0 | 5 | 5 | 10
Jimmy, Chris, Bill, Eric | Final Conceptual Architecture | 0 | 0 | 5 | 0 | 5
Chris, Bill, Eric | Final Detailed Design | 0 | 0 | 7 | 0 | 7
Jimmy, Chris, Bill, Eric | Customer Delivery | 0 | 0 | 0 | 4 | 4
Chris, Bill, Eric | Executor Implementation | 0 | 5 | 0 | 0 | 5
Chris, Bill, Eric | Single Step Progression | 5 | 5 | 0 | 0 | 10
Chris, Bill, Eric | Pausing On Event | 4 | 0 | 4 | 0 | 8
Chris, Bill, Eric | Generate Additional ODIN Test Cases | 0 | 0 | 5 | 5 | 10
Chris, Bill, Eric | Change ONA prefix | 1 | 0 | 0 | 0 | 1
Chris, Bill, Eric | User Manual | 0 | 0 | 10 | 10 | 20
Chris, Bill, Eric | Add Comprssion to Preprocessor | 0 | 5 | 0 | 0 | 5
Chris, Bill, Eric | Correct ODIN Extensions | 3 | 0 | 4 | 0 | 7
Chris, Bill, Eric | Usablilty Testing | 0 | 0 | 0 | 10 | 10
Chris, Bill, Eric | Connection Abstraction | 2 | 4 | 4 | 0 | 10
Jimmy, Chris, Bill, Eric | Peer and Self Evaluation | 0 | 0 | 0 | 2 | 2
Jimmy, Chris, Bill, Eric | Individual Design | 0 | 0 | 0 | 2 | 2
Jimmy, Chris, Bill, Eric | Customer Meetings | 2 | 2 | 2 | 4 | 10
Jimmy | Status Reports | 2 | 2 | 2 | 4 | 10
Total Estimated Hours Remaining |  | 160 | 120 | 80 | 40 | 0